## Summary
Module | Technology
Frontend | React + Vite + Tailwind CSS
Backend | Node.js + Express
Database | MongoDB Atlas
Realtime | Socket.IO
Documents | PDF upload + secure download
Auth | JWT + role-based access control
Storage | MongoDB + local uploads (extensible to cloud object storage)
Estimate
Hours
PM (15%)
QA (15%)
Total
Assumptions
Client will provide production cloud/hosting accounts and credentials for deployment.
WordPress website will expose contact form payload to configured webhook endpoint.
Static categories and schemes are maintained in DB and changed via controlled admin updates.
Any paid third-party service cost (SMS/email/push/storage) will be managed by client.
Estimate covers current CRM scope and excludes future phase enhancements.

## Features
Module | Highlights | Hours
Platform & Architecture | • Ability to set up scalable React + Vite frontend and Node + Express backend architecture. • Ability to configure secure environment, database connection, and startup validation. • Ability to define reusable API/error standards and static catalog data foundation.
Authentication & Access Control | • Ability to authenticate users securely with role-based access control. • Ability to persist sessions and enforce protected route behavior. • Ability to enforce assignment-based task execution permissions.
User Administration | • Ability for admin to manage user lifecycle and role assignment. • Ability to maintain safe admin controls and prevent lockout scenarios. • Ability to support assignment workflows through active user directory.
Lead Management | • Ability to capture leads from manual entry and WordPress contact forms. • Ability to track full lead communication history with notes and call logs. • Ability to classify and filter leads by HOT, WARM, COLD, and CONVERTED buckets.
Lead Conversion & Client Onboarding | • Ability to convert qualified leads to clients with controlled confirmation flow. • Ability to auto-create linked project with static milestone/task structure. • Ability to preserve conversion audit history and references across entities.
Client Management | • Ability to create and manage clients independently of lead conversion. • Ability to auto-create project when a client is onboarded directly. • Ability to search clients and review linked project context quickly.
Project Management Core | • Ability to manage projects through clear stage-based execution tabs. • Ability to present operational metrics and stage health in one workspace. • Ability to enforce role-aware visibility for admin and users.
Milestones & Tasks | • Ability to structure project delivery into milestones and actionable tasks. • Ability to assign work, due dates, and priorities with controlled rules. • Ability to auto-track task and stage progress based on real execution actions.
Task Collaboration & Documents | • Ability for teams to collaborate inside each task through comments and files. • Ability to capture author/date metadata for every collaboration event. • Ability to secure document access and keep project records audit-friendly.
Automation & Workflow Engine | • Ability to automate milestone and project status synchronization. • Ability to drive stage progression based on execution outcomes. • Ability to keep operational counters and audit history consistently updated.
Notifications & Live Activity | • Ability to broadcast real-time updates for concurrent users. • Ability to control user visibility of live activity from admin settings. • Ability to provide browser notifications and read-state aware notification feed.
Dashboard & Reporting | • Ability to monitor operations using KPI and pending-work dashboards. • Ability to capture response, conversion, and execution metrics for analysis. • Ability to keep audit/reporting data ready for future advanced reports.
Settings & Catalog Configuration | • Ability for admin to control system behavior through settings pages. • Ability to store global configuration in MongoDB for centralized control. • Ability to serve static category/scheme catalogs for all business workflows.
UI UX System & Frontend Quality | • Ability to deliver consistent enterprise-grade UI patterns across all modules. • Ability to keep list-first workflows clean using inline filters and modal forms. • Ability to improve readability using badges, spacing, typography, and smart datetime UX.
QA, Security Hardening & Release Readiness | • Ability to validate critical workflows end-to-end before production release. • Ability to harden security controls across auth, webhooks, and file operations. • Ability to prepare release with operational confidence and traceability.
Invoice Management & PDF Experience | • Ability to operate invoices through dedicated details and PDF pages with source-aware back navigation. • Ability to view invoice PDF in-app with zoom, rotate, reset, and download controls. • Ability to maintain professional PDF layout integrity for line-item rendering and readability.
Total

## Platform & Architecture
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Platform & Architecture | Environment Setup | Ability to create production-ready FE and BE project structure |  | 6 | 4 | 2
|  | Ability to manage environment variables for FE and BE securely |  | 4 | 4 | 2
| Database Bootstrap | Ability to connect MongoDB Atlas with startup failure handling |  | 2 | 6 | 2
| Data Standards | Ability to generate unique IDs for leads, clients, and projects |  | 2 | 6 | 2
| API Standards | Ability to enforce centralized error handling and HTTP response consistency |  | 2 | 6 | 3
| Catalog Foundation | Ability to seed static categories and scheme data into MongoDB |  | 1 | 6 | 3
| Runtime Baseline | Ability to standardize run/build commands and port configuration |  | 2 | 2 | 1

## Auth & Access Control
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Authentication & Access Control | Authentication | Ability to log in with secure credential validation and JWT session |  | 8 | 8 | 4
|  | Ability to hydrate authenticated user session across page refresh |  | 4 | 4 | 2
|  | Ability to log out securely and invalidate local auth context |  | 3 | 2 | 1
| Password Security | Ability to change password using current-password verification |  | 6 | 6 | 3
| Role Access | Ability to restrict admin-only actions by role middleware |  | 3 | 6 | 2
| Task Authorization | Ability to allow task updates only for assignee or admin |  | 4 | 8 | 4
| Project Visibility | Ability to limit non-admin project visibility to assigned work |  | 4 | 8 | 3
| Reporting Access | Ability to restrict reporting summary endpoints to admin-only visibility

## User Administration
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
User Administration | User Listing | Ability to view user table with role, status, and search filters |  | 8 | 4 | 2
| User Creation | Ability to create new users with role and secure password rules |  | 8 | 6 | 4
| User Lifecycle | Ability to activate or deactivate users with confirmation dialogs |  | 6 | 6 | 3
| Admin Safety | Ability to prevent disabling or demoting the last active admin |  | 2 | 6 | 4
|  | Ability to prevent self-disable on current logged-in admin account |  | 2 | 4 | 2
| Assignment Support | Ability to provide assignable active users for task assignment |  | 2 | 4 | 3
| Audit Trail | Ability to capture user management actions in system activity logs |  | 2 | 5 | 4

## Lead Management
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Lead Management | Lead Intake | Ability to create leads manually with core company and contact fields |  | 8 | 6 | 4
|  | Ability to receive submitted WordPress contact forms via secured webhook |  | 2 | 6 | 6
| Lead Listing | Ability to list leads with search, source, and status filters |  | 10 | 8 | 4
| Lead Buckets | Ability to show HOT/WARM/COLD/CONVERTED tabs with quick filtering |  | 8 | 6 | 4
| Lead Timeline | Ability to add lead notes with author and timestamp entries |  | 6 | 6 | 5
| Call Logging | Ability to log call date, time, duration, and discussion summary |  | 6 | 6 | 5
| Follow-up Rules | Ability to auto-calculate lead heat based on update recency rules |  | 2 | 8 | 4
| Lead SLAs | Ability to capture first-response and follow-up metrics for reporting |  | 2 | 6 | 5
| Lead Search | Ability to search by company, contact person, and mobile |  | 4 | 4 | 2
| Lead Intake Wizard | Ability to create leads using 4-step guided flow (Basic Details -> Location & Profile -> Financial Scope -> Operations)
| Step Validation | Ability to validate mandatory fields before moving to next lead-create step

## Lead Conv & Client Onboard
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Lead Conversion & Client Onboarding | Conversion Flow | Ability to convert a lead into a client from lead detail page |  | 6 | 8 | 6
|  | Ability to auto-create project immediately after successful conversion |  | 2 | 6 | 8
| Data Mapping | Ability to map category, scheme, department, and values during conversion |  | 4 | 6 | 6
| Lead State | Ability to move converted lead to CONVERTED tab automatically |  | 4 | 4 | 4
| Audit & Traceability | Ability to log conversion event with lead, client, and project references |  | 2 | 6 | 6
| Workflow Safety | Ability to keep conversion workflow validated against duplicate operations |  | 1 | 4 | 5

## Client Management
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Client Management | Client Onboarding | Ability to create client with organization and contact profile |  | 8 | 6 | 4
|  | Ability to auto-create project from direct client creation flow |  | 3 | 5 | 6
| Client Listing | Ability to list and search clients with key relationship fields |  | 8 | 6 | 3
| Data Linkage | Ability to preserve source lead reference for converted clients |  | 2 | 4 | 4
| Client Context | Ability to show linked project count and active stage snapshot |  | 4 | 5 | 3
| Timeline | Ability to capture client creation and linkage events for reporting trail |  | 2 | 5 | 4

## Project Management Core
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Project Management Core | Project Listing | Ability to view project table with filters by stage and assignment |  | 8 | 6 | 4
| Project Workspace | Ability to open project detail with stage tabs and progress summary |  | 12 | 10 | 6
| Stage Management | Ability for admin to change project stage with confirmation dialog |  | 6 | 6 | 4
| Stage Indicators | Ability to color-code stage tabs by DONE/IN_PROGRESS/PENDING |  | 6 | 4 | 3
| Execution Metrics | Ability to show milestone, task, and completion counters |  | 4 | 4 | 4
| Project Timeline | Ability to render project timeline events with actor and smart date |  | 6 | 6 | 5
| Access Scope | Ability to show all projects for admin and assigned-only projects for users |  | 3 | 6 | 4

## Milestones & Tasks
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Milestones & Tasks | Milestone Management | Ability to create milestones under selected project stages |  | 6 | 6 | 5
|  | Ability to update milestone due date and stage mapping |  | 4 | 4 | 4
| Task Management | Ability to create task with title, description, priority, and due date |  | 8 | 7 | 5
| Task Assignment | Ability to assign task owner and update assignee when required |  | 4 | 5 | 5
| Task Execution Rules | Ability to auto-mark task IN_PROGRESS on first comment or upload |  | 2 | 6 | 4
| Task Completion Rules | Ability to block completion when required document is missing |  | 2 | 6 | 4
| Status Automation | Ability to auto-complete milestone once all child tasks are closed |  | 2 | 7 | 5
| Task UI | Ability to display color-coded capsules for priority, status, assignee, and due |  | 8 | 5 | 3
| Pending Queue | Ability to show role-aware pending task queue on dashboard |  | 6 | 5 | 4

## Task Collab & Documents
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Task Collaboration & Documents | Task Detail View | Ability to open task in detailed modal with execution context |  | 8 | 5 | 3
| Comments | Ability to add comments and display commenter with timestamp |  | 6 | 6 | 5
|  | Ability to render ordered comment history for multi-user collaboration |  | 4 | 4 | 4
| Document Upload | Ability to upload PDF documents per task execution step |  | 6 | 6 | 6
| Document Access | Ability to download attachments through authorized secure route |  | 4 | 5 | 6
| Permission Guard | Ability to enforce assignee/admin permission on comments and uploads |  | 2 | 6 | 5
| Timeline Integration | Ability to write collaboration events into project timeline stream |  | 2 | 5 | 5

## Invoice Mgmt & PDF Exp
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Invoice Management & PDF Experience | Invoice Details Workspace | Ability to open invoices on dedicated detail page instead of popup
| Navigation Context | Ability to return users to source page using back navigation context (list <-> details <-> PDF)
| PDF Viewer Page | Ability to open invoice PDF in dedicated in-app page from list and details
| PDF Controls | Ability to zoom/rotate/reset/download invoice PDF from viewer toolbar
| PDF Layout Integrity | Ability to keep line-item table within page margins with wrapped descriptions
| PDF Table Structure | Ability to render line-item columns as Description, Unit Price, Qty, Amount
| Modal Validation UX | Ability to keep create-invoice validation messages inside modal context

## Automation & Workflow Engine
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Automation & Workflow Engine | Status Sync | Ability to recalculate milestone status using child task statuses |  | 1 | 7 | 6
| Stage Progression | Ability to auto-advance project stage after stage completion |  | 1 | 7 | 6
| Project Completion | Ability to auto-close project when all milestones are completed |  | 1 | 6 | 5
| Activity Stats | Ability to auto-recompute task, milestone, comment, and document counters |  | 1 | 6 | 5
| Audit Events | Ability to write system timeline events for automated state changes |  | 1 | 6 | 6
| Queue Sync | Ability to refresh pending work queues based on assignment and status changes |  | 2 | 6 | 5

## Notifications & Live Activity
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Notifications & Live Activity | Realtime Infrastructure | Ability to initialize and maintain socket-based event channel |  | 2 | 7 | 6
| Event Security | Ability to authenticate socket connection using JWT identity |  | 1 | 5 | 5
| Notification Delivery | Ability to send user-scoped live events for workflow updates |  | 4 | 6 | 6
| Live Activity Panel | Ability to show collapsible right-side live activity panel |  | 8 | 5 | 3
| Visibility Controls | Ability to toggle live activity for users while admin sees always |  | 6 | 5 | 5
| Browser Alerts | Ability to trigger browser notifications for key updates |  | 4 | 4 | 4
| Notification Inbox | Ability to list notifications and mark as read by recipient |  | 6 | 5 | 5

## Dashboard & Reporting
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Dashboard & Reporting | KPI Dashboard | Ability to show lead, client, project, and pending task counters |  | 8 | 6 | 4
|  | Ability to show lead conversion rate and average first response time |  | 6 | 6 | 5
| Execution Insights | Ability to show stage distribution and completion progress |  | 6 | 5 | 4
| Pending Work | Ability to display pending task queue with assignee and deadline |  | 6 | 5 | 4
| Report Metrics | Ability to capture communication statistics for management reporting |  | 2 | 6 | 6
| Audit Readiness | Ability to persist event trail fields required for audit and future reports |  | 1 | 6 | 6
| Role-Based Dashboards | Ability to show admin analytics dashboard and user-specific work dashboard separately
| User Workboard | Ability to present assigned actionable tasks for users without admin-only analytics widgets

## Settings & Catalog Config
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
Settings & Catalog Configuration | Admin Settings | Ability to manage live activity configuration for user visibility |  | 6 | 5 | 5
| Admin Security | Ability to update admin password from secure settings form |  | 6 | 5 | 4
| Config Storage | Ability to persist and read global app settings from MongoDB |  | 2 | 5 | 6
| Catalog Seed | Ability to maintain static categories and schemes in database records |  | 2 | 6 | 6
| Catalog APIs | Ability to fetch category and scheme master data in FE forms |  | 3 | 5 | 4
| Access Security | Ability to restrict settings and catalog controls to admin role |  | 1 | 4 | 4

## UI UX & Frontend Quality
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
UI UX System & Frontend Quality | Layout System | Ability to implement consistent sidebar, topbar, and dashboard shell |  | 12 | 4 | 2
| Modal UX | Ability to keep create/edit actions in modals with confirmations |  | 10 | 4 | 2
| Table UX | Ability to align search/filter controls above tables for maximum data space |  | 10 | 4 | 2
| Badge System | Ability to apply status-based color capsules across tables and task lists |  | 8 | 4 | 2
| Date UX | Ability to display smart datetime rules (Today, Yesterday, weekday, full date) |  | 8 | 4 | 2
| Sidebar Behavior | Ability to keep sidebar fixed with user details/signout pinned at bottom |  | 8 | 3 | 1
| Timeline UX | Ability to paginate timeline records and maintain responsive scroll behavior |  | 8 | 4 | 2
| Modal Error UX | Ability to show validation and API errors within active modal surface
| Pagination UX | Ability to standardize table pagination controls using << and >> with aligned page status
| Brand Alignment | Ability to align login/sidebar branding visuals with provided logo asset and color tone

## QA Security & Release
Module | Submodule | Tasks (Ability to...) | UI | FE | BE | Integration
QA, Security Hardening & Release Readiness | API Validation | Ability to validate request payloads on all write endpoints |  | 6 | 8 | 8
| Security Controls | Ability to enforce webhook key and auth guard reliability checks |  | 5 | 6 | 6
| Workflow Testing | Ability to test lead-to-client-to-project lifecycle end-to-end |  | 6 | 8 | 8
| Permission Testing | Ability to verify role and assignment controls across modules |  | 5 | 6 | 6
| Upload Testing | Ability to test document upload/download and completion guards |  | 5 | 6 | 6
| Release Readiness | Ability to complete final smoke checks and go-live readiness list |  | 4 | 5 | 5