## Summary
Module | Technology
App | Flutter v3+
CMS | React v19+
Bakend | Nodejs v20+
DB | Mongo Cloud
Hosting | AWS
|  | Estimate | ~
|  | Hours | 2866
|  | PM | 429.9
|  | QA | 429.9
3725.8
Assunmption
The client will provide and maintain all required cloud accounts (AWS / GCP / Firebase or equivalent) for hosting, storage, and backend services.
The client will provide access to Apple App Store and Google Play Console, including certificates, provisioning profiles, and release permissions.
The client will provide credentials, subscriptions, and commercial licenses for any selected third-party services such as live streaming, maps, analytics, email, and push notifications.
The development team will select standard industry tools (e.g., Agora/Twilio for live video, Google Maps/Mapbox for location, FCM/APNS for push notifications) unless the client specifies alternatives in writing.
Any paid third-party tool costs (usage, bandwidth, API calls, storage, or subscriptions) will be borne by the client.
The client will provide necessary access to Scentle’s website, APIs, or tracking mechanisms required for e-commerce linking and attribution.
The client will approve the final list of third-party vendors during technical design before development begins.

## Features
Module | Highlights | Hours
Platform & Architecture -Identity, Data & Security | • Ability to create base project structure (mobile, web, backend, admin, CMS). • Ability to define system architecture and API boundaries. • Ability to configure Dev, Staging, and Production environments. • Ability to manage environment variables and configurations.• Ability for users to sign up, log in, and log out. • Ability to implement role-based access (User, Instructor, Company Admin, Super Admin). • Ability to design core database models (users, content, journeys, groups). • Ability to secure data, tokens, and user privacy. | 95
Content Library | • Ability to upload and manage content via CMS. • Ability to tag content for B2C or specific B2B companies. | 160
Wellness Journey (Thematic Paths) | • Ability for users to choose a journey (Sleep, Anxiety, Back Pain, etc.). • Ability to curate content based on selected journey. | 169
Multimedia Content | • Ability to consume content in multiple formats. • Ability to mix educational and inspirational content. | 84
Video Streaming (On-demand + Live) | • Ability to watch recorded videos. • Ability to join live streaming sessions. | 206
User Generated Content | • Ability for users to upload media. • Ability to share experiences with others. | 80
Community & Groups | • Ability to create/join groups. • Ability to collaborate and share ideas. | 200
B2B Company Workspace | • Ability for each company to have a private space. • Ability to share internal experiences. | 150
Personalized Preferences | • Ability to choose preferred content types. • Ability to set preferred notification time. | 54
Music & Healing Sounds | • Ability to stream wellness music. • Ability to match sounds to journey type. | 99
Personalized Programs | • Ability to design user-specific programs. • Ability to sequence content for users. | 163
Notifications & Email | • Ability to send push notifications. • Ability to send personalized emails. | 102
Instructor / Educator Portal | • Ability for instructors to upload videos. • Ability to manage their sessions. | 135
Live Interactive Sessions | • Ability to host live classes. • Ability for users to participate in real time. | 188
Location Sharing & Pin Drop | • Ability to share live location (opt-in). • Ability to drop location pins. | 152
Scentle E-commerce Integration | • Ability to link content to products. • Ability to redirect to purchase pages. | 155
User Profile & Journey Tracking | • Ability to maintain a profile. • Ability to track journey progress. | 90
Analytics & Engagement | • Ability to track views, likes, shares. • Ability to generate engagement reports. | 212
Admin CMS | • Ability to approve/reject content. • Ability to manage users, instructors, companies. | 140
Roles & Access Control | • Ability to define roles (Admin, Instructor, User, Company). • Ability to control permissions per role. | 232
2866

## Project Setup
Module | Submodule | Tasks (…) | UI | FE | BE | Integration
Core Platform & Identity | Environment Setup | configure Dev, Staging, Production environments |  | 0 | 4 | 0
|  | manage environment variables securely |  | 2 | 2 | 0
| API Architecture | define RESTcontract standards |  | 2 | 2 | 4
|  | implement pagination, filtering, sorting |  | 2 | 4 | 4
| Authentication | sign up via email/password |  | 4 | 4 | 2
|  | verify email via OTP or magic link |  | 2 | 2 | 4
|  | log in via JWT / OAuth |  | 2 | 2 | 2
|  | refresh access tokens securely |  | 2 | 2 | 2
|  | log out and revoke tokens |  | 2 | 1 | 1
| Forgot Password | trigger password reset |  | 4 | 2 | 1
|  | validate reset tokens |  | 2 | 2 | 2
| Security | encrypt sensitive data at rest |  | 2 | 4 | 2
| Logging & Monitoring | capture structured logs |  | 4 | 4 | 2
|  | monitor API health and latency |  | 0 | 4 | 0
95

## Content Library
Module | Submodule | Tasks | UI | FE | BE | Integration
Content Library | Admin Upload | Ability to upload images, videos, audio, text |  | 8 | 6 | 4
|  | Ability to store files in cloud storage (S3/GCS) |  | 0 | 4 | 0
| Metadata | Ability to add title, description, tags |  | 2 | 2 | 2
|  | Ability to assign to journeys |  | 2 | 2 | 1
|  | Ability to set language, region, category |  | 12 | 8 | 8
| Visibility Rules | Ability to mark content as B2C-only |  | 1 | 1 | 2
|  | Ability to assign content to specific companies |  | 1 | 1 | 1
| Company Curation | Ability for company admin to select content |  | 4 | 4 | 6
|  | Ability to approve/reject content for employees |  | 4 | 4 | 4
| Publishing | Ability to publish/unpublish content |  | 4 | 2 | 2
|  | Ability to schedule publishing time |  | 2 | 4 | 4
| End User Feed | Ability to fetch personalized content feed |  | 6 | 6 | 4
|  | Ability to filter by journey |  | 2 | 4 | 4
| Media Rendering | Ability to render article viewer |  | 1 | 1 | 2
|  | Ability to render image gallery |  | 2 | 2 | 2
|  | Ability to render video player |  | 2 | 2 | 2
|  | Ability to render audio player |  | 2 | 2 | 2
160

## Wellness Journey
Module | Submodule | Tasks | UI | FE | BE | Integration
Wellness Journey | Admin Setup | Ability to create new journeys |  | 12 | 8 | 12
|  | Ability to edit journey metadata |  | 2 | 4 | 4
| Content Mapping | Ability to attach content to journeys |  | 2 | 2 | 2
|  | Ability to reorder content sequence |  | 4 | 2 | 2
| Rules Engine | Ability to define recommendation rules |  | 4 | 4 | 4
|  | Ability to auto-suggest next content |  | 4 | 6 | 6
| Company Config | Ability for company to enable/disable journeys |  | 4 | 2 | 2
| User Selection | Ability for user to select journey |  | 4 | 2 | 1
| Journey Feed | Ability to generate journey-specific feed |  | 4 | 12 | 8
| Progress Tracking | Ability to track completion per item |  | 4 | 8 | 6
|  | Ability to view progress UI |  | 20 | 4 | 4
169

## Multimedia Content
Module | Submodule | Tasks | UI | FE | BE | Integration
Multimedia | Media Renderer | Ability to detect media type dynamically |  | 2 | 2 | 4
|  | Ability to render rich text articles |  | 6 | 2 | 2
|  | Ability to stream video |  | 12 | 6 | 4
|  | Ability to play audio |  | 8 | 4 | 4
| Course System | Ability to enroll in course |  | 4 | 4 | 2
|  | Ability to track lesson completion |  | 2 | 6 | 4
|  | Ability to show course progress |  | 2 | 2 | 2
84

## Video Streaming
Module | Submodule | Tasks | UI | FE | BE | Integration
Video Streaming | Video Player | Ability to support play/pause/seek |  | 12 | 4 | 2
|  | Ability to support captions/subtitles |  | 4 | 2 | 2
| Live Setup | Ability to create live session |  | 24 | 16 | 16
|  | Ability to schedule live streams |  | 2 | 6 | 8
| Live Viewing | Ability to join live stream |  | 12 | 16 | 8
|  | Ability to show viewer count |  | 4 | 4 | 2
| Chat | Ability to send live messages |  | 12 | 8 | 16
|  | Ability to moderate chat |  | 6 | 12 | 8
206

## UGC
Module | Submodule | Tasks | UI | FE | BE | Integration
UGC | Upload | Ability to upload images/videos |  | 6 | 4 | 4
|  | Ability to compress media before upload |  | 2 | 2 | 2
| Moderation | Ability for admin to approve/reject |  | 12 | 6 | 4
|  | Ability to flag inappropriate content |  | 8 | 4 | 4
| Community Feed | Ability to display UGC posts |  | 8 | 4 | 4
|  | Ability to allow likes/comments on UGC |  | 2 | 2 | 2
80

## Communities and groups
Module | Submodule | Tasks | UI | FE | BE | Integration
Community & Groups | Group Creation | Ability for user/company to create a group
Ability to set group name, description, cover image
Ability to define group type (Public / Private / Invite-only)
Ability to assign group admin(s)
Group Membership | Join / Leave | Ability for users to request to join
Ability for admin to approve/reject requests
Ability for user to leave group anytime
Ability to view member list
Group Home Feed | Feed View | Ability to view group feed timeline
Ability to sort feed (Latest / Trending / Top)
Ability to filter by Posts / Media / Courses
Posts (Forum Core) | Create Post | Ability to create text post
Ability to attach images/videos to post
Ability to tag post with topic/category
| Edit/Delete | Ability to edit own post
Ability to delete own post
Comments | Commenting | Ability to comment on posts
Ability to reply to comments (threaded replies)
Ability to edit/delete own comment
Reactions & Engagement | Likes | Ability to like posts
Ability to like comments
Ability to view like count
| Bookmarks | Ability to bookmark/save posts
| Share | Ability to share post within app
Moderation | Content Review | Ability for group admin to moderate posts
Ability to remove inappropriate content
Ability to mute/block users in group
Notifications | Group Alerts | Ability to notify members on new post
Ability to notify when someone comments
Ability for user to control notification settings
Search & Discovery | Search | Ability to search posts inside group
Ability to search groups globally
Group Courses | Course Access | Ability to view group-specific courses
Ability to enroll in group course
Ability to track completion
Roles inside Group | Role Mgmt | Ability to assign roles (Admin / Moderator / Member)
Ability to define permissions per role
Analytics (Optional but important) | Group Insights | Ability to view active users
Ability to see most liked posts
Ability to see engagement stats
200

## B2B Company Workspace
Module | Submodule | Tasks | UI | FE | BE | Integration
B2B Workspace | Company Onboarding | Ability to create company account
Ability to add company branding
| Employee Mgmt | Ability to add/remove employees
Ability to assign roles
| Content Curation | Ability to select approved content
Ability to block certain content
| Preferences | Ability to set notification timing
Ability to customize journeys
| Analytics | Ability to view engagement reports
| Employee View | Ability to access private company feed
150

## Personalized Preferences
Module | Submodule | Tasks | UI | FE | BE | Integration
Preferences | Content Selection | Ability to choose topics |  | 6 | 4 | 2
| Notification Timing | Ability to set preferred time |  | 6 | 2 | 2
| Frequency | Ability to set notification frequency |  | 4 | 4 | 4
| Sync | Ability to sync across devices |  | 4 | 8 | 8
54

## Music and healing sounds
Module | Submodule | Tasks | UI | FE | BE | Integration
Personalized Preferences | Preference Onboarding | Ability to collect preferences during first login |  | 2 | 2 | 2
|  | Ability to present topic selection UI (Sleep, Anxiety, etc.) |  | 2 | 2 | 2
|  | Ability to store initial preferences in profile |  | 2 | 4 | 2
Content Preferences | Topic Selection | Ability to select multiple wellness topics |  | 1 | 1 | 1
|  | Ability to update topics anytime in settings |  | 1 | 1 | 1
|  | Ability to preview sample content per topic |  | 1 | 1 | 1
Notification Preferences | Timing | Ability to choose preferred notification time |  | 1 | 1 | 1
|  | Ability to set different times for weekdays/weekends |  | 2 | 2 | 2
| Frequency | Ability to set daily/weekly frequency |  | 2 | 4 | 2
|  | Ability to mute notifications temporarily |  | 1 | 1 | 1
Journey Preferences | Default Journey | Ability to set a primary wellness journey |  | 4 | 2 | 4
|  | Ability to change journey anytime |  | 4 | 6 | 6
Device Sync | Cross-device | Ability to sync preferences across devices |  | 2 | 2 | 4
Reset & Defaults | Reset | Ability to reset preferences to defaults |  | 2 | 2 | 2
| Admin Defaults | Ability for admin to define default preferences |  | 4 | 4 | 2
99

## Personalized Programs
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Personalized Programs | Program Builder (Admin) | Ability to create structured wellness programs |  | 24 | 16 | 16
|  | Ability to name and describe programs |  | 2 | 2 | 2
| Content Assignment | Ability to attach videos/articles/courses |  | 2 | 2 | 2
|  | Ability to reorder program steps |  | 6 | 4 | 6
Scheduling Engine | Timeline | Ability to schedule content by day/time |  | 2 | 2 | 2
|  | Ability to send automated reminders |  | 2 | 6 | 1
User Enrollment | Join Program | Ability for user to enroll in a program |  | 4 | 6 | 4
|  | Ability to see daily tasks |  | 4 | 4 | 4
Progress Tracking | Completion | Ability to mark tasks as completed |  | 2 | 6 | 2
|  | Ability to show progress dashboard |  | 8 | 6 | 4
Analytics | User Insights | Ability to see completion rates |  | 2 | 4 | 4
163

## Notifications & Email
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Notifications & Email | Push System | Ability to send real-time push notifications |  | 0 | 12 | 4
|  | Ability to target users by journey |  | 0 | 6 | 4
Email System | Templates | Ability to create email templates |  | 12 | 6 | 4
|  | Ability to personalize emails per company |  | 4 | 4 | 4
Rules Engine | Automation | Ability to trigger reminders automatically |  | 2 | 4 | 4
|  | Ability to set conditional rules (if/then) |  | 8 | 4 | 4
User Controls | Opt-in/out | Ability to enable/disable notifications |  | 2 | 2 | 4
|  | Ability to manage email preferences |  | 4 | 2 | 2
102

## Instructor Educator Portal
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Instructor Portal | Authentication | Ability for instructor to log in |  | 24 | 24 | 12
|  | Ability to reset password |  | 2 | 2 | 2
Content Upload | Videos | Ability to upload recorded videos |  | 6 | 4 | 4
|  | Ability to add titles/descriptions |  | 1 | 1 | 1
Live Sessions | Scheduling | Ability to schedule live classes |  | 4 | 4 | 2
|  | Ability to edit/cancel sessions |  | 4 | 4 | 2
Dashboard | Analytics | Ability to view engagement stats |  | 8 | 12 | 6
|  | Ability to see viewer counts |  | 2 | 2 | 2
135

## Live Interactive Sessions
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Live Sessions | Host Panel | Ability to start live stream |  | 12 | 24 | 16
|  | Ability to manage participants |  | 6 | 6 | 6
Viewer Experience | Join | Ability to join live session |  | 4 | 8 | 6
|  | Ability to see live video feed |  | 6 | 6 | 6
Interaction | Chat | Ability to send messages |  | 4 | 4 | 4
|  | Ability to moderate chat |  | 4 | 12 | 12
| Q&A | Ability to submit questions |  | 8 | 8 | 8
| Polls | Ability to run live polls |  | 6 | 6 | 6
188

## Location Sharing & Pin Drop
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Location | Permissions | Ability to request location permission |  | 16 | 12 | 8
|  | Ability to explain why location is used |  | 1 | 1 | 1
Live Sharing | Share | Ability to share live location |  | 16 | 16 | 8
|  | Ability to stop sharing anytime |  | 2 | 2 | 2
Pin Drop | Create Pin | Ability to drop pin on map |  | 16 | 8 | 6
|  | Ability to add label to pin |  | 1 | 1 | 1
Map View | Display | Ability to render interactive map |  | 12 | 4 | 12
|  | Ability to zoom/pan map |  | 2 | 2 | 2
152

## Scentle E-commerce Integration
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
E-commerce Integration | Product Linking | Ability to attach products to content |  | 16 | 12 | 12
|  | Ability to display product preview |  | 2 | 2 | 2
Deep Links | Navigation | Ability to open product in browser/app |  | 4 | 1 | 1
| Tracking | Ability to pass referral parameters |  | 4 | 2 | 2
Redirect Flow | Click-to-buy | Ability to redirect to Scentle site |  | 1 | 1 | 1
| Session Handling | Ability to return to app smoothly |  | 6 | 6 | 8
Analytics | Click Tracking | Ability to track product clicks |  | 24 | 24 | 24
155

## User Profile & Journey Tracking
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
User Profile | View Profile | Ability to view profile details |  | 4 | 4 | 4
|  | Ability to view profile photo |  | 1 | 4 | 4
Edit Profile | Update | Ability to edit name, bio, photo |  | 2 | 2 | 2
|  | Ability to update preferences |  | 1 | 1 | 1
Journey History | Timeline | Ability to see past journeys |  | 6 | 6 | 4
|  | Ability to see completed content |  | 4 | 4 | 4
Badges & Rewards | Earn Badges | Ability to earn badges |  | 4 | 8 | 8
| Display | Ability to showcase badges |  | 4 | 4 | 4
90

## Analytics & Engagement
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Analytics | Admin Dashboard | Ability to view system KPIs |  | 24 | 24 | 24
|  | Ability to filter by company/user |  | 2 | 2 | 2
Content Metrics | Engagement | Ability to track views/likes |  | 4 | 8 | 8
|  | Ability to track shares/comments |  | 4 | 6 | 6
B2B Reports | Company Insights | Ability to generate reports |  | 24 | 24 | 24
| Export | Ability to export CSV/PDF |  | 4 | 16 | 6
212

## Admin CMS
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Admin CMS | Content Mgmt | Ability to upload/edit content |  | 12 | 12 | 12
|  | Ability to moderate UGC |  | 12 | 8 | 8
User Mgmt | Accounts | Ability to manage users |  | 8 | 8 | 6
|  | Ability to deactivate users |  | 2 | 2 | 2
Instructor Mgmt | Access | Ability to approve instructors |  | 8 | 8 | 8
|  | Ability to revoke access |  | 2 | 2 | 2
Publishing | Scheduling | Ability to schedule posts |  | 6 | 6 | 6
140

## Roles & Access Control
Module | Submodule | Tasks (Ability to…) | UI | FE | BE | Integration
Roles & Access | Role Definition | Ability to create roles |  | 12 | 12 | 16
|  | Ability to edit permissions |  | 8 | 8 | 6
Assignment | User Roles | Ability to assign roles to users |  | 4 | 4 | 4
| Company Roles | Ability to assign company roles |  | 6 | 6 | 6
Restrictions | Feature Control | Ability to block features per role |  | 8 | 12 | 6
| Data Access | Ability to limit data visibility |  | 8 | 12 | 4
Audit | Logs | Ability to review access logs |  | 24 | 24 | 24
| Compliance | Ability to export audit trail |  | 6 | 6 | 6
232